## Sheet1
Description | Start date | Duration
Collect Arabic data with Tashkeel | 2016-07-25 | 30
Test Mbrola tools | 42583 | 7
Split each file to sentence | 2016-09-01 | 21
Remove tashkeel and samples from the sentences | 2016-10-01 | 3
Do Modawwana code | 2016-10-15 | 14
Improve the Modawwana code | 2016-11-02 | 7
Run the files in the Modawwana code | 2016-11-10 | 14
Do frequency code | 2016-12-01 | 7
Run the files in frequency code | 2016-12-09 | 14
Calculate the number of occurrence of two words with each other | 2017-01-01 | 21
Python code | 2017-01-15 | 7
Python database | 2017-02-01 | 7
Update Naïve base code | 2017-03-01 | 2
Update Modawana word code | 2017-03-15 | 2
Update Modawana char code | 2017-03-17 | 2
Add indexing to all DB | 2017-04-01 | 4
Add new data to frequency char DB(2-2) | 2017-04-01 | 70
Add new data to frequency word DB(2-2) | 2017-04-01 | 70
Add new data to frequency char DB(2-1) | 2017-04-01 | 70
Add new data to frequency word DB(2-1) | 2017-04-01 | 70
Add new data to frequency char DB(1-3) | 2017-04-01 | 70
Add new data to frequency word DB(1-3) | 2017-04-01 | 70
Add new data to frequency char DB(3-3) | 2017-04-01 | 70
Add new data to frequency word DB(3-3) | 2017-04-01 | 70
Add new data to Modawana char DB | 2017-04-05 | 60
Add new data to Modawana word DB | 2017-04-05 | 60
Ge the accuracy to each window | 2017-05-20 | 20
Get the statistics to each data base | 2017-06-01 | 3
Make the model code to read from DB | 2015-05-01 | 3
Make the model code to write to DB | 2017-05-01 | 7
Make simple website | 2017-06-15 | 4